## Slide 1: Travis County PROP A: Child Care and Afterschool And Summer Programming
Next Steps for Implementation
Presentation to Joint Subcommittee: 12/06/2024

## Slide 2: Background
On November 5, 2024, Travis County Voters approved a 2.5 cent tax rate increase that will generate over $75 million to increase access to affordable and high-quality child care and afterschool/summer programming and related services for low-income families and develop and administer related workforce and economic development programs.

## Slide 3: Overview of Strategies
Four strategies will serve as a baseline for developing and implementing expanded child care and afterschool and summer programming in Travis County.
Strategy 1: Expand slots for infants/toddlers (ages 0-3) and for afterschool and summer programming (PreK-12th grade)
Strategy 2: Expand non-traditional hour care
Strategy 3: Build quality and capacity
Strategy 4: Business Government Alliance for business contributions to employee child care costs by matching public funds

## Slide 4: Structure and Staffing
HHS Program Staff:
Manager, Planners, Community Engagement, Communications
Staff to ensure checks and balances in:
County Auditor’s Office
Purchasing Department
County Attorney’s Office
HHS Finance
A start up focus is hiring staff to carry out the County’s work.
Travis County
Travis County
Attorney’s Office
Travis County HHS
Community Advisory Committee
Travis County Auditor’s Office
Travis County Commissioners Court
Contractors
Third-Party Evaluator
Travis County Purchasing Department

## Slide 5: Community Engagement
Listening sessions
Early 2025
Gather input from stakeholders to inform program design
Advisory Council
Incorporate community voice in the planning and on-going implementation of Voter-Approved funds​
Communications Plan
Updates about implementation progress
Information about available services
Name and branding

## Slide 6: Program Implementation
Implement services using a phased approach throughout 2025 and 2026.
Near term investments: Explore expanding existing County contracts to begin providing services in 2025 and lower the wait for families on waitlists
Implement Strategies: Design programs and procure services in the four strategies to expand services in 2026
  Refine program design using strategy outlines, examples from other communities, and community input
  Seek approval of program policies by Commissioner’s Court
  Plan for procurement and develop scopes of work for the services the County seeks to procure
  Procure services including administrator(s), service providers, third-party evaluator

## Slide 7: Ongoing Program Operations
Selected contractors will be responsible for the day-to-day program operations
County staff will oversee and manage contracts to ensure compliance
Third-party evaluator will evaluate programs and report outcomes to stakeholders and the Commissioners Court.
County staff, contractors, the Advisory Council, and other stakeholders, will partner to maximize resources, identify gaps in services, prevent duplication of services, and refine the strategies as needed to improve service delivery.

## Slide 8: Key Milestone Targets
Staff hired
April 2025
Near-term investments (Expand current contracts)
Spring -Summer 2025
Contracts for 0-3 Child Care Slots
June 2026
Contracts for services in all 4 strategies
Dec 2026
Community input summary, program design recommendations, & TCCC policy approval
Summer 2025
Begin releasing solicitations for services
Fall 2025