## Bond Program Financials
| 1 |  | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10
Proposed 2017 Bond Budget-to Actual (a/o January 31, 2025)
|  | CONSTRUCTION COSTS | 2: AS APPROVED BOND BOOK; 5: BUDGET AMENDMENTS; 7: TOTALS TO DATE
|  | Projects | TOTAL COST FULLY MARKED UP | Unallocated Budgets | Budget a/o December 31, 2024 | Program Contingency Alloc Less than $250k | Program Contingency Alloc More than $250k | Budget a/o January 31, 2025 | Actuals | Commitments | Balance
1 |  | Modernization Projects:
2 |  | Ann Richards | 70000000 | 61113000 | 61131422 |  |  | 61131422 | 61131005 | 415 | 2
3 |  | Austin HS | 23468000 | 20488000 | 21688060 |  |  | 21688060 | 21688057 | 0 | 3
4 |  | Bear Creek ES (New Southwest ES) | 36167000 | 31575000 | 35405763 |  |  | 35405763 | 35405761 | 0 | 2
5 |  | Blazier Relief ES/MS | 50000000 | 43652000 | 42026973 |  |  | 42026973 | 42021658 | 0 | 5315
6 |  | Bowie HS ** | 88000000 | 76827000 | 73734165 |  |  | 73734165 | 73511804 | 78823 | 143538
7 |  | Brentwood | 35764000 | 31223000 | 37679288 |  |  | 37679288 | 37511111 | 49790 | 118387
8 |  | Casis | 35150000 | 30687000 | 38707107 |  |  | 38707107 | 38706561 | 0 | 546
9 |  | Doss ES | 43000000 | 37541000 | 37885214 |  |  | 37885214 | 37885212 | 0 | 2
10 |  | Eastside Vertical Modernization (Sanchez) | 25000000 | 21631000 | 26490561 |  |  | 26490561 | 26333015 | 2283 | 155263
11 |  | Govalle | 32499000 | 28373000 | 29822251 |  |  | 29822251 | 29822248 | 0 | 3
12 |  | Hill ES | 17000000 | 14842000 | 14080316 |  |  | 14080316 | 14080312 | 0 | 4
13 |  | LBJ ECHS Medical HS | 22000000 | 19207000 | 19226701 |  |  | 19226701 | 18451080 | 17040 | 758581
14 |  | LBJ Vertical Modernization (Norman-Sims) | 25000000 | 21631000 | 27606644 |  |  | 27606644 | 27266525 | 27220 | 312899
15 |  | Menchaca *** | 33300000 | 29072000 | 9142910 |  |  | 9142910 | 9142911 | 0 | -1
16 |  | Modernized Eastside HS @ Anderson | 80000000 | 69843000 | 80942000 |  |  | 80942000 | 80844850 | 77997 | 19153
17 |  | Murchison (plus targeted) | 24620000 | 21494000 | 24350180 |  |  | 24350180 | 24350180 | 0 | 0
18 |  | General Marshall MS (New MS in Northeast Austin) | 60958000 | 53219000 | 58309000 |  |  | 58309000 | 55276153 | 387435 | 2645412
19 |  | Rosedale | 40000000 | 34921000 | 40255209 |  |  | 40255209 | 40253136 | 1983 | 90
20 |  | T. A. Brown * | 30797000 | 26887000 | 16499180 |  |  | 16499180 | 16499182 | 0 | -2
21 |  | Subtotal Modernization Projects | 772723000 | 674226000 | 694982944 | 0 | 0 | 694982944 | 690180761 | 642986 | 4159197
22 |  | Targeted Projects:
23 |  | Akins High-Critical Facility Deficiencies | 9941000 | 8601375 | 8308883 |  |  | 8308883 | 8071477.94 | 135923.25 | 101481.81
24 |  | Akins High-Rigging Repairs | 244000 | 211111 | 427 |  |  | 427 | 427 | 0 | 0
25 |  | Allison Elementary-Critical Facility Deficiencies | 845000 | 731132 | 810374 |  |  | 810374 | 810375.94 | 0 | -1.94
26 |  | Andrews Elementary-Critical Facility Deficiencies | 208000 | 179969 | 7600 |  |  | 7600 | 7600 | 0 | 0
27 |  | Austin High-Critical Facility Deficiencies | 3712000 | 3211781 | 2688217 |  |  | 2688217 | 2688217.01 | 0 | -0.01
28 |  | Austin High-Rigging Repairs | 244000 | 211111 | 657978 |  |  | 657978 | 657976.38 | 0 | 1.62
29 |  | Bailey Middle-Critical Facility Deficiencies | 4938000 | 4272568 | 4312664 |  |  | 4312664 | 3912857.27 | 281884.73 | 117922
30 |  | Baldwin Elementary-Critical Facility Deficiencies | 217000 | 187758 | 99505 |  |  | 99505 | 99505.17 | 0 | -0.17
31 |  | Baranoff Elementary-Critical Facility Deficiencies | 2654000 | 2296354 | 255696 |  |  | 255696 | 255696.18 | 0 | -0.18
32 |  | Barbara Jordan Elementary-Critical Facility Deficiencies | 961000 | 831499 | 958540 |  |  | 958540 | 941840.19 | 1095 | 15604.81
33 |  | Barrington Elementary-Critical Facility Deficiencies | 1204000 | 1041752 | 1081247 |  |  | 1081247 | 1050862.01 | 0 | 30384.99
34 |  | Barton Hills Elementary-Critical Facility Deficiencies | 165000 | 142765 | 76807 |  |  | 76807 | 74114.6 | 2691.25 | 1.15
35 |  | Becker Elementary-Critical Facility Deficiencies | 1181000 | 1021852 | 1140528 |  |  | 1140528 | 1157615.41 | 0 | -17087.41
36 |  | Bedichek Middle-Critical Facility Deficiencies | 4062000 | 3514614 | 4747598 |  |  | 4747598 | 3857853.49 | 60581.41 | 829163.1
37 |  | Bertha Sadler Means Young Women's Leadership-Critical Facility Deficiencies | 2086000 | 1804896 | 1280349 |  |  | 1280349 | 1206997.58 | 1074 | 72277.42
38 |  | Blackshear Elementary-Critical Facility Deficiencies | 1377000 | 1191438 | 2101836 |  |  | 2101836 | 1790684.85 | 179532.29 | 131618.86
39 |  | Blanton Elementary-Critical Facility Deficiencies | 431000 | 372922 | 401141 |  |  | 401141 | 401139.07 | 0 | 1.93
40 |  | Blazier Intermediate School 900 Wing Build Out | 0 | 0 | 3993098 |  |  | 3993098 | 3122504.88 | 309506.05 | 561087.07
41 |  | Boone Elementary-Critical Facility Deficiencies | 2151000 | 1861136 | 2685488 |  |  | 2685488 | 2214838.45 | 0 | 470649.55
42 |  | Bowie High-Critical Facility Deficiencies | 1444000 | 1249410 | 2269277 |  |  | 2269277 | 1583691.07 | 0 | 685585.93
43 |  | Bryker Woods Elementary-Critical Facility Deficiencies | 201000 | 173913 | 135100 |  |  | 135100 | 135029.56 | 70 | 0.44
44 |  | Burger Athletic Complex-Critical Facility Deficiencies | 1265000 | 1094533 | 1182785 |  |  | 1182785 | 1145751.79 | 35 | 36998.21
45 |  | Burnet Middle-Critical Facility Deficiencies | 2157000 | 1866329 | 1641021 |  |  | 1641021 | 1637014.45 | 4003.75 | 2.8
46 |  | Campbell Elementary-Critical Facility Deficiencies | 672000 | 586646 | 789363 |  |  | 789363 | 767240.81 | 22121.5 | 0.69
47 |  | Casey Elementary-Critical Facility Deficiencies | 786000 | 680082 | 726392 |  |  | 726392 | 726392.4 | 0 | -0.4
48 |  | Clayton Elementary -Critical Facility Deficiencies | 671000 | 580578 | 586026 |  |  | 586026 | 497796.57 | 29923.85 | 58305.58
49 |  | Clifton Center-Critical Facility Deficiencies | 375000 | 324467 | 700092 |  |  | 700092 | 700092.21 | 0 | -0.21
50 |  | Construction Management-Critical Facility Deficiencies | 0 | 0 | 4499684 |  |  | 4499684 | 4339033.52 | 0 | 160650.48
51 |  | Cook Elementary-Critical Facility Deficiencies | 2113000 | 1828259 | 922998 | -1 |  | 922997 | 922997.84 | 0 | -0.84
52 |  | Covington Middle-Critical Facility Deficiencies | 3184000 | 2754932 | 2102980 |  |  | 2102980 | 2102979.74 | 0 | 0.26
53 |  | Covington Middle-Rigging Repairs | 244000 | 211111 | 550000 |  |  | 550000 | 532056.44 | 0 | 17943.56
54 |  | Covington MS - FA Acad. Reinv. | 1503000 | 1300000 | 1736000 |  |  | 1736000 | 1695690.76 | 1046.53 | 39262.71
55 |  | Cowan Elementary-Critical Facility Deficiencies | 4592000 | 3973197 | 2834480 |  |  | 2834480 | 2834477.52 | 0 | 2.48
56 |  | Crockett High-Critical Facility Deficiencies | 12331000 | 10669306 | 4637224 |  |  | 4637224 | 4299830.85 | 34792 | 302601.15
57 |  | Crockett High-Rigging Repairs | 244000 | 211111 | 702200 |  |  | 702200 | 662727.94 | 0 | 39472.06
58 |  | Cunningham Elementary-Critical Facility Deficiencies | 1352000 | 1169806 | 1117128 |  |  | 1117128 | 1117128.36 | 0 | -0.36
59 |  | Davis Elementary-Critical Facility Deficiencies | 893000 | 772662 | 1019019 |  |  | 1019019 | 1016596.93 | 2419.56 | 2.51
60 |  | Dawson Elementary-Critical Facility Deficiencies | 1576000 | 1363620 | 1404404 |  |  | 1404404 | 1210805.16 | 1275 | 192323.84
61 |  | Delco Activity Center-Critical Facility Deficiencies | 417000 | 360807 | 617082 |  |  | 617082 | 458724.54 | 0 | 158357.46
62 |  | Dobie Middle-Critical Facility Deficiencies | 2157000 | 1866330 | 2568345 | -1 |  | 2568344 | 2568344.03 | 0 | -0.03
63 |  | Galindo Elementary-Critical Facility Deficiencies | 845000 | 731131 | 1533414 |  |  | 1533414 | 1393971.88 | 72648.62 | 66793.5
64 |  | Garcia Young Men's Leadership Academy (effective 09-01-14)-Critical Facility Deficiencies | 3387000 | 2930577 | 2958080 |  |  | 2958080 | 66696 | 0 | 2891384
65 |  | Garza Independence-Critical Facility Deficiencies | 87000 | 75275 | 28310 |  |  | 28310 | 28309.71 | 0 | 0.29
66 |  | Gorzycki Middle-Critical Facility Deficiencies | 742000 | 642009 | 642009 |  |  | 642009 | 540849.04 | 0 | 101159.96
67 |  | Graham Elementary-Critical Facility Deficiencies | 2014000 | 1742601 | 1742601 |  |  | 1742601 | 1459180.09 | 20122.81 | 263298.1
68 |  | Guerrero Thompson Elementary-Critical Facility Deficiencies | 490000 | 423968 | 928445 |  |  | 928445 | 897674.95 | 0 | 30770.05
69 |  | Gullett Elementary-Critical Facility Deficiencies | 349000 | 301969 | 439591 |  |  | 439591 | 439589.95 | 0 | 1.05
70 |  | Harris Elementary-Critical Facility Deficiencies | 1689000 | 1456193 | 1234846 |  |  | 1234846 | 1234664.3 | 0 | 181.7
71 |  | Hart Elementary-Critical Facility Deficiencies | 1984000 | 1716642 | 2700302 |  |  | 2700302 | 2256212.29 | 182909.12 | 261180.59
72 |  | Highland Park Elementary-Critical Facility Deficiencies | 1737000 | 1502927 | 1141555 |  |  | 1141555 | 1141554.83 | 0 | 0.17
73 |  | Hill Elementary-Critical Facility Deficiencies | 724000 | 626438 | 838224 |  |  | 838224 | 838223.81 | 0 | 0.19
74 |  | House Park | 6000000 | 5191000 | 8099775 |  |  | 8099775 | 670242.81 | 136465.2 | 7293066.99
75 |  | Houston Elementary-Critical Facility Deficiencies | 2912000 | 2519588 | 2650876 |  |  | 2650876 | 2650876.22 | 0 | -0.22
76 |  | Jaime Padron Elementary-Critical Facility Deficiencies | 571000 | 494054 | 1347 |  |  | 1347 | 1346.57 | 0 | 0.43
77 |  | Joslin Elementary-Critical Facility Deficiencies | 2016000 | 1744330 | 954031 |  |  | 954031 | 920807.1 | 0 | 33223.9
78 |  | Kealing Middle-Critical Facility Deficiencies | 1880000 | 1626655 | 1905298 |  |  | 1905298 | 1855075.05 | 0 | 50222.95
79 |  | Kealing Middle-Rigging Repairs | 244000 | 211111 | 39815 |  |  | 39815 | 39815.12 | 0 | -0.12
80 |  | Kiker Elementary-Critical Facility Deficiencies | 748000 | 647201 | 558080 |  |  | 558080 | 558076.75 | 0 | 3.25
81 |  | Kocurek Elementary-Critical Facility Deficiencies | 1106000 | 956959 | 622346 |  |  | 622346 | 622341.99 | 0 | 4.01
82 |  | L C Anderson High-Critical Facility Deficiencies | 8139000 | 7042208 | 6615679 |  |  | 6615679 | 5761198.83 | 770979.7 | 83500.47
83 |  | L C Anderson High-Rigging Repairs | 244000 | 211111 | 0 |  |  | 0 | 6662.35 | 0 | -6662.35
84 |  | Lamar Middle-Critical Facility Deficiencies | 6717000 | 5811834 | 3410474 |  |  | 3410474 | 3410474.25 | 0 | -0.25
85 |  | Langford Elementary-Critical Facility Deficiencies | 265000 | 229288 | 276748 |  |  | 276748 | 276745.33 | 0 | 2.67
86 |  | LASA move to Eastside | 4000000 | 3461000 | 5402486 |  |  | 5402486 | 5276508.28 | 43397.87 | 82579.85
87 |  | LASA-Critical Facility Deficiencies | 3822000 | 3306958 | 3293708 | 4651 |  | 3298359 | 3298357.83 | 0 | 1.17
88 |  | LBJ Comprehensive High School-Critical Facility Deficiencies | 1573000 | 1361026 | 34300 |  |  | 34300 | 14300 | 0 | 20000
89 |  | Lee Elementary-Critical Facility Deficiencies | 760000 | 657584 | 526211 |  |  | 526211 | 526211.29 | 0 | -0.29
90 |  | Life Safety | 19042000 | 16476000 | 24452446 |  |  | 24452446 | 13104548.06 | 1086460.71 | 10261437.23
91 |  | Linder Elementary-Critical Facility Deficiencies | 1952000 | 1688953 | 1880328 |  |  | 1880328 | 1829844.31 | 3500 | 46983.69
92 |  | Lively Middle (Fulmore)-Critical Facility Deficiencies | 3868000 | 3346758 | 3778872 |  |  | 3778872 | 3564961.36 | 0 | 213910.64
93 |  | Lively Middle (Fulmore)-Rigging Repairs | 244000 | 211111 | 0 |  |  | 0 | 0 | 0 | 0
94 |  | Maplewood Elementary-Critical Facility Deficiencies | 685000 | 592691 | 797538 |  |  | 797538 | 775393.76 | 0 | 22144.24
95 |  | Martin Jr. High-Critical Facility Deficiencies | 4023000 | 3480872 | 2409803 |  |  | 2409803 | 2409803.21 | 0 | -0.21
96 |  | Mathews Elementary-Critical Facility Deficiencies | 886000 | 766605 | 676406 |  |  | 676406 | 676405.62 | 0 | 0.38
97 |  | McBee Elementary-Critical Facility Deficiencies | 1123000 | 971666 | 921806 |  |  | 921806 | 921806 | 0 | -1.1642e-10
98 |  | McCallum High-Critical Facility Deficiencies | 2398000 | 2074853 | 2074853 |  |  | 2074853 | 2221904.74 | 0 | -147051.74
99 |  | McCallum/Lamar MS - FA Acad. Reinv. | 10797000 | 9342000 | 14497270 |  |  | 14497270 | 13778505.9 | 12440.72 | 706323.38
100 |  | Mendez Middle-Critical Facility Deficiencies | 1131000 | 978590 | 1590541 |  |  | 1590541 | 1328987.78 | 249649.92 | 11903.3
101 |  | Mendez Middle-Rigging Repairs | 244000 | 211111 | 204404 |  |  | 204404 | 86491.45 | 0 | 117912.55
102 |  | Mills Elementary-Critical Facility Deficiencies | 772000 | 667965 | 1409732 |  |  | 1409732 | 1352742.14 | 53818.1 | 3171.76
103 |  | Murchison Middle-Critical Facility Deficiencies | 0 | 0 | 48300 |  |  | 48300 | 48300 | 0 | 0
104 |  | Navarro ECHS (Lanier)-Critical Facility Deficiencies | 4823000 | 4173065 | 3975000 |  |  | 3975000 | 3875625.33 | 39326.61 | 60048.06
105 |  | Nelson Field /Bus Terminal-Critical Facility Deficiencies | 468000 | 404933 | 504746 |  |  | 504746 | 504746.64 | 0 | -0.64
106 |  | Northeast ECHS (Reagan)-Critical Facility Deficiencies | 2023000 | 1750386 | 3623348 |  |  | 3623348 | 3623114.63 | 232.5 | 0.87
107 |  | Northeast ECHS (Reagan)-Rigging Repairs | 244000 | 211112 | 646451 |  |  | 646451 | 635580.88 | 0 | 10870.12
108 |  | Northeast ECHS(Reagan) -Career Launch Acad. Reinv. | 2402000 | 2078000 | 432311 |  |  | 432311 | 432310.22 | 0 | 0.78
109 |  | O. Henry Middle-Critical Facility Deficiencies | 1964000 | 1699337 | 1709241 |  |  | 1709241 | 1709240.51 | 0 | 0.49
110 |  | Oak Hill Elementary-Critical Facility Deficiencies | 799000 | 691330 | 537729 |  |  | 537729 | 540692.38 | 0 | -2963.38
111 |  | Oak Springs Elementary-Critical Facility Deficiencies | 90000 | 77873 | 5980 |  |  | 5980 | 5980 | 0 | 0
112 |  | Odom Elementary-Critical Facility Deficiencies | 3818000 | 3303499 | 2676233 |  |  | 2676233 | 2676232.25 | 0 | 0.75
113 |  | Ortega Elementary-Critical Facility Deficiencies | 1261000 | 1091070 | 793297 |  |  | 793297 | 793297.08 | 0 | -0.08
114 |  | Overton Elementary -Critical Facility Deficiencies | 827000 | 715556 | 584558 |  |  | 584558 | 584559.96 | 0 | -1.96
115 |  | Palm Elementary-Critical Facility Deficiencies | 1279000 | 1106649 | 1147661 |  |  | 1147661 | 1147660.42 | 0 | 0.58
116 |  | Paredes Middle-Critical Facility Deficiencies | 2064000 | 1785860 | 3298889 |  |  | 3298889 | 882173.34 | 946002.43 | 1470713.23
117 |  | Patton Elementary-Critical Facility Deficiencies | 1336000 | 1155963 | 1173304 |  |  | 1173304 | 1001457 | 158880.31 | 12966.69
118 |  | Pease Elementary-Critical Facility Deficiencies | 467000 | 404067 | 408000 |  |  | 408000 | 28478.75 | 0 | 379521.25
119 |  | Pecan Springs Elementary-Critical Facility Deficiencies | 3517000 | 3043060 | 1987945 |  |  | 1987945 | 1987944.03 | 0 | 0.97
120 |  | Perez Elementary -Critical Facility Deficiencies | 610000 | 527800 | 229669 |  |  | 229669 | 213814.48 | 3855 | 11999.52
121 |  | Performing Arts Center-Critical Facility Deficiencies | 18000 | 15575 | 29469 |  |  | 29469 | 29467.19 | 0 | 1.81
122 |  | Pickle Elementary-Critical Facility Deficiencies | 1642000 | 1420729 | 1800000 |  |  | 1800000 | 1660961.11 | 0 | 139038.89
123 |  | Pillow Elementary-Critical Facility Deficiencies | 2408000 | 2083506 | 1838135 |  |  | 1838135 | 1539174.59 | 0 | 298960.41
124 |  | Pleasant Hill Annex-Critical Facility Deficiencies | 135000 | 116808 | 640000 |  |  | 640000 | 243663.35 | 333344.65 | 62992
125 |  | Pleasant Hill Elementary-Critical Facility Deficiencies | 2437000 | 2108598 | 1487443 |  |  | 1487443 | 1487443.86 | 0 | -0.86
126 |  | Reilly Elementary-Critical Facility Deficiencies | 2860000 | 2474597 | 1624461 | -1 |  | 1624460 | 1624461.89 | 0 | -1.89
127 |  | Ridgetop Elementary-Critical Facility Deficiencies | 1997000 | 1727893 | 1382971 |  |  | 1382971 | 1284575.69 | 28502.19 | 69893.12
128 |  | Rodriguez Elementary-Critical Facility Deficiencies | 988000 | 854861 | 991193 |  |  | 991193 | 991192.94 | 0 | 0.06
129 |  | Saegert Trans Center-Critical Facility Deficiencies | 383000 | 331389 | 362942 |  |  | 362942 | 359096.03 | 0 | 3845.97
130 |  | South Bus Terminal (New Bus Terminal)-Critical Facility Deficiencies | 52000 | 44995 | 2520 |  |  | 2520 | 2520 | 0 | 0
131 |  | St. Elmo Elementary-Critical Facility Deficiencies | 260000 | 224965 | 239327 |  |  | 239327 | 239327.75 | 0 | -0.75
132 |  | Summitt Elementary-Critical Facility Deficiencies | 733000 | 634222 | 1030321 |  |  | 1030321 | 996408.88 | 7887.12 | 26025
133 |  | Sunset Valley Elementary-Critical Facility Deficiencies | 2067000 | 1788458 | 1913742 | -19312 |  | 1894430 | 1894428.74 | 0 | 1.26
134 |  | Travis Heights Elementary-Critical Facility Deficiencies | 967000 | 836688 | 940000 |  |  | 940000 | 932152.37 | 0 | 7847.63
135 |  | Travis High-Critical Facility Deficiencies | 7275000 | 6294640 | 5429695 |  |  | 5429695 | 5038096.47 | 5679.18 | 385919.35
136 |  | Uphaus Early Childhood Center (Linder)-Critical Facility Deficiencies | 73000 | 63162 | 6875 |  |  | 6875 | 6875 | 0 | 0
137 |  | Walnut Creek Elementary-Critical Facility Deficiencies | 2584000 | 2235788 | 1613291 |  |  | 1613291 | 1613291.53 | 0 | -0.53
138 |  | Webb Middle -Critical Facility Deficiencies | 2096000 | 1813548 | 3307685 |  |  | 3307685 | 3305945.06 | 0 | 1739.94
139 |  | Widen Elementary-Critical Facility Deficiencies | 1344000 | 1162887 | 1093195 |  |  | 1093195 | 1093193.18 | 0 | 1.82
140 |  | Williams Elementary-Critical Facility Deficiencies | 431000 | 372922 | 759428 |  |  | 759428 | 759422 | 0 | 6
141 |  | Winn Elementary-Critical Facility Deficiencies | 1317000 | 1139526 | 987347 |  |  | 987347 | 987345.27 | 0 | 1.73
142 |  | Wooldridge Elementary-Critical Facility Deficiencies | 558000 | 482805 | 612624 |  |  | 612624 | 573087.65 | 7645 | 31891.35
143 |  | Wooten Elementary-Critical Facility Deficiencies | 2480000 | 2145802 | 508306 |  |  | 508306 | 508305.5 | 0 | 0.5
144 |  | Zilker Elementary-Critical Facility Deficiencies | 986000 | 853132 | 320222 |  |  | 320222 | 320222.79 | 0 | -0.79
145 |  | Subtotal Targeted Projects | 241091000 | 208601000 | 224325980 | -14664 | 0 | 224311316 | 189696213.6 | 5231722.93 | 29383379.47
146 |  | Non Construction:
147 |  | Bond Carry Costs | 30000000 | 30000000 | 18054201 |  |  | 18054201 | 11465748.85 | 0 | 6588452.15
148 |  | Campus/Co-Curriculum Master Planning | 1513000 | 1513000 | 2326375 |  |  | 2326375 | 2628024.94 | 0 | -301649.94
149 |  | Furniture | 5000000 | 5000000 | 4414275 |  |  | 4414275 | 2739002.58 | 1481.24 | 1673791.18
150 |  | Police Equipment | 4408000 | 4408000 | 3648559 |  |  | 3648559 | 3148190.02 | 254233.22 | 246135.76
151 |  | Police Equipment-Transportation | 3100000 | 3100000 | 3859441 |  |  | 3859441 | 3759991 | 0 | 99450
152 |  | Technology | 55500000 | 55500000 | 54690340 |  |  | 54690340 | 50193618.62 | 1920834.84 | 2575886.54
153 |  | Transportation | 21400000 | 21400000 | 21400000 |  |  | 21400000 | 20547413.17 | 0 | 852586.83
154 |  | Copying and Printing | 0 | 1518000 | 1518000 |  |  | 1518000 | 242156 | 13502.92 | 1262341.08
155 |  | Legal Services | 0 | 380000 | 735796 |  |  | 735796 | 1702243.52 | 0 | -966447.52
156 |  | Misc. Services - Construction Inspection | 0 | 1139000 | 1468969 |  |  | 1468969 | 2503363.38 | 0 | -1034394.38
157 |  | Newspaper Advertising | 0 | 949000 | 74000 |  |  | 74000 | 30964.37 | 0 | 43035.63
158 |  | Permits and Fees | 0 | 3416000 | 1521130 |  |  | 1521130 | 1180360.75 | 39956.41 | 300812.84
159 |  | Program Management | 0 | 49004000 | 54045850 |  |  | 54045850 | 66633893.58 | 22051.92 | -12610095.5
160 |  | Safety Consulting | 0 | 759000 | 762995 |  |  | 762995 | 727870.58 | 0 | 35124.42
161 |  | Subtotal Non Construction | 120921000 | 178086000 | 168519931 | 0 | 0 | 168519931 | 167502841.36 | 2252060.55 | -1234970.91
162
163 |  | Program Contingency | 0 | 73822000 | 3155145 | 14664 | 0 | 3169809 | 0 | 0 | 3169809 | 3754701
164 |  | Unused Surplus | 2: 0; 3: 0; 10: 0
165
166 |  | Grand Total | 1134735000 | 1134735000 | 1090984000 | 0 | 0 | 1090984000 | 1047379815.96 | 8126769.48 | 35477414.56
167 |  | Estimated Real Estate Revenue | 2: -40000000; 3: -40000000; 4: -40000000; 7: -40000000
168 |  | Previous Bond-2008 Bond (T. A. Brown) * | 2: -10751000; 3: -10751000
169 |  | Previous Bond-2008 Bond (Bowie) ** | 2: -10000000; 3: -10000000
170 |  | Previous Bond-2013 Bond (Menchaca) *** | 2: -23000000; 3: -23000000
171 |  | 2017 Bond Total Amount | 1050984000 | 1050984000 | 1050984000 | 0 | 0 | 1050984000 | 1047379815.96 | 8126769.48 | -4522585.44
Notes:
All numbers are as of January 31, 2025.
Targeted and Non Construction amounts include multiple projects.
* At present, $12.1m of 2008 Bond funds were used to supplement the 2017 Bond funds for the project. A total of $11.8m has been spent to date from 2008 Bond funds. The 2017 Bond budget has not been
reduced by the amount of the 2008 Bond funds used. The adjustment of the 2017 Bond budget will be made in financial closeout at the end of the project.
** At present, $10.0m of 2008 Bond funds were used to supplement the 2017 Bond funds for the project. A total of $10m has been spent to date from 2008 Bond funds. The 2017 Bond budget has not been
reduced by the amount of the 2013 Bond funds used. The adjustment of the 2017 Bond budget will be made in financial closeout at the end of the project.
*** At present, $23.0m of 2013 Bond funds were used to supplement the 2017 Bond funds for the project. A total of $23m has been spent to date from 2013 Bond funds. The 2017 Bond budget has not been
reduced by the amount of the 2013 Bond funds used. The adjustment of the 2017 Bond budget will be made in financial closeout at the end of the project.
See Previous Bond schedule for more details on the T. A. Brown, Menchaca and Bowie projects.
Contingency funds to be prioritized for overcrowding relief for the Northwest, Blazier, Cowan and Baranoff communities.
Numbers may not add due to rounding.

## Bond Program Amendments
Bond Program Start to Date Budget Amendments - 2017 Bond Funds Only |  | Total To Date: | 70652191 | 23795812 |  | -49238176
Difference
January 2025 - 2017 Bond Budget Amendments
Contingency Transfers
| Sunset Valley ES - Transferring cost savings from targeted project back into Program Contingency |  | -19312
| Reily ES - Transferring cost savings from closed targeted project back into Program Contingency |  | -1
| Cook ES - Transferring cost savings from closed targeted project back into Program Contingency |  | -1
| Dobie MS - Transferring cost savings from closed targeted project back into Program Contingency |  | -1
| LASA - Additional Funds for Targeted Project 200036 |  | 4651
| Total January 2025 |  | -14664
December 2024 - 2017 Bond Budget Amendments
Contingency Transfers
| Covington MS - Additional Funds for Project 200007 |  | 72087
| Total December 2024 |  | 72087
November 2024 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
October 2024 - 2017 Bond Budget Amendments
Contingency Transfers
| Baldwin ES - Transferring cost savings from targeted project back into Program Contingency |  | -88253
| Blanton ES - Transferring cost savings from targeted project back into Program Contingency |  | -14564
| Burnet MS - Transferring cost savings from targeted project back into Program Contingency |  | -225308
| Clifton Center - Transferring cost savings from targeted project back into Program Contingency |  | -94510
| Cowan ES - Transferring cost savings from targeted project back into Program Contingency |  | -1138717
| Davis ES - Transferring cost savings from targeted project back into Program Contingency |  | -18082
| Harris ES - Transferring cost savings from targeted project back into Program Contingency |  | -249927
| Kocurek ES - Transferring cost savings from targeted project back into Program Contingency |  | -374887
| LASA - Transferring cost savings from targeted project back into Program Contingency |  | -421903
| Nelson Bus Terminal - Transferring cost savings from targeted project back into Program Contingency |  | -118424
| St. Elmo ES - Transferring cost savings from targeted project back into Program Contingency |  | -7487
| Uphaus Early - Transferring cost savings from targeted project back into Program Contingency |  | -56287
| Winn ES - Transferring cost savings from targeted project back into Program Contingency |  | -162871
| Total October 2024 |  | -2971220
September 2024 - 2017 Bond Budget Amendments
Contingency Transfers
| Hart ES - Additional Funds for Project 210011 |  | 351000
| Total September 2024 |  | 351000
August 2024 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
July 2024 - 2017 Bond Budget Amendments
Contingency Transfers
| Blackshear ES - Additional Funds for Project 210008 |  | 340025
| Total July 2024 |  | 340025
June 2024 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Casis ES-Environmental Services and Field Assessments Project 200002 |  | 10731
| Austin High School - Additional funds for Rigging Repairs |  | 749
| Campbell ES - Additional Funds for Project 220003 |  | 4611
| Baranoff Elementary - Transferring cost savings from project back into Program Contingency |  | -20000
| Martin Middle School - Transferring cost savings from project back into Program Contingency |  | -917846
| Total June 2024 |  | -921755
May 2024 - 2017 Bond Budget Amendments
Contingency Transfers
| Anderson High School - Additional funds for Project 220024 |  | 680000
| Pleasant Hill Annex - Additional funds for Demo Project 190045 |  | 240000
| House Park - Additional Funds for Project 210034 |  | 1828458
| Bowie High School - Transferring cost savings from project back into Program Contingency |  | -29630
| Mendez Middle School - Additional Architecture Services for Project 210023 |  | 9350
| Total May 2024 |  | 2728178
April 2024 - 2017 Bond Budget Amendments
Contingency Transfers
| Summitt Elementary - Critical Facility Deficiency |  | 67887
| Additional funds for master planning professional services. |  | 10653
| Hart Elementary-Critical Facility Deficiencies |  | 613188
| Targeted Projects -Transferring cost savings from various projects back into Program Contingency |  | -219623
| Targeted Projects -Transferring cost savings from various projects back into Program Contingency |  | -3585012
| Austin High School - Additional funds for Lighting Control Panel. |  | 34778
| Blazier Relief ES 900 Wing Build Out. |  | 1276498
| Total April 2024 |  | -1801631
March 2024 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
February 2024 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Blazier Relief ES - Additional funds for HVAC controls. |  | 40000
| Blazier Relief ES 900 Wing Build Out. |  | 2522000
| Guerrero-Thompson ES - Critical Facility Deficiency HVAC work. |  | 32972
| Mills ES - To supplement funding of Critical Facility Deficiency project. |  | 4900
| Districtwide professional services for AISD Project Development Manual aligning with Educational Specifications for Athletics, CTC, and Fine Arts. |  | 193000
| Total February 2024 |  | 2792872
January 2024 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Rosedale- Additional funds needed for access gate repair. |  | 10000
| Total January 2024 |  | 10000
December 2023 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Bear Creek ES-Transferring cost savings from project back into Program Contingency. |  | -11249
| Modernized Blazier Relief ES-Transferring cost savings from project back into Program Contingency. |  | -108527
| Modernized Brentwood ES-Transferring cost savings from project back into Program Contingency. |  | -200000
| Modernized Casis ES-Transferring cost savings from project back into Program Contingency. |  | -416760
| Modernized Doss ES-Transferring cost savings from project back into Program Contingency. |  | -1000
| Modernized Hill ES-Transferring cost savings from project back into Program Contingency. |  | -11684
| Modernized Eastside HS @ Anderson - Additional funds need to complete change order. |  | 110000
| Modernized Rosedale-Transferring cost savings from project back into Program Contingency. |  | -576791
| Modernized T. A. Brown ES-Transferring cost savings from project back into Program Contingency. |  | -1305820
| Total December 2023 |  | -2521831
November 2023 - 2017 Bond Budget Amendments
Contingency Transfers
| Additional funds for districtwide consulting services for Critical Facility Deficiency projects. |  | 939714
| Jordan ES, Mills ES, Guerrero Thompson ES, Barrington ES, & Mendez MS-To supplement Critical Facility Deficiency budgets. |  | 1070872
| Modernized Ann Richards HS-Transferring cost savings from project back into Program Contingency. |  | -981578
| Modernized Murchison MS-Transferring cost savings from project back into Program Contingency. |  | -268820
| Modernized Austin HS-Transferring cost savings from project back into Program Contingency. |  | -1299940
| Total November 2023 |  | -539752
October 2023 - 2017 Bond Budget Amendments
Contingency Transfers
| Additional funds for districtwide survey services. |  | 79519
| Modernized Rosedale- Additional funds needed for installation of missed duct heaters. |  | 50000
| Modernized Doss ES -Transferring cost savings from project back into Program Contingency. |  | -14786
| Modernized Menchaca ES -Transferring cost savings from project back into Program Contingency. |  | -9090
| Modernized Govalle ES -Transferring cost savings from project back into Program Contingency. |  | -10749
| Total October 2023 |  | 94894
September 2023 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
August 2023 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
July 2023 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
June 2023 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
May 2023 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Rosedale -Transferring cost savings from project back into Program Contingency. |  | -50000
| Modernized LBJ -Transferring cost savings from project back into Program Contingency. |  | -100000
| Modernized Hill -Transferring cost savings from project back into Program Contingency. |  | -65000
| Modernized Doss -Transferring cost savings from project back into Program Contingency. |  | -65000
| Blazier IS 900 wing finish-out. |  | 233100
| Total May 2023 |  | -46900
April 2023 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
March 2023 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
February 2023 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Ann Richards -Transferring cost savings from project back into Program Contingency. |  | -800000
| Modernized Bear Creek -Transferring cost savings from project back into Program Contingency. |  | -320000
| Modernized Blazier Relief ES/MS -Transferring cost savings from project back into Program Contingency. |  | -120000
| Modernized Bowie -Transferring cost savings from project back into Program Contingency. |  | -850000
| Modernized Brentwood - Additional funds needed for architect fee increase for new PCB. |  | 500000
| Modernized Casis ES -Transferring cost savings from project back into Program Contingency. |  | -500000
| Modernized Doss ES -Transferring cost savings from project back into Program Contingency. |  | -275000
| Modernized Govalle ES -Transferring cost savings from project back into Program Contingency. |  | -90000
| Modernized Hill ES -Transferring cost savings from project back into Program Contingency. |  | -685000
| Modernized Murchison MS -Transferring cost savings from project back into Program Contingency. |  | -75000
| Modernized Marshall MS- Additional funds needed for construction and design fees which exceed original budget and additional funds for FF&E. |  | 4340000
| Modernized Rosedale -Transferring cost savings from project back into Program Contingency. |  | -900000
| *Adjustments to complete Targeted Projects. |  | 16073574
| Total February 2023 |  | 16298574
January 2023 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Blazier Relief ES/MS -Transferring cost savings from project back into Program Contingency. |  | -1650000
| Modernized Eastside HS @ Anderson - Additional funds need to complete change order. |  | 1250000
| Transferring cost savings from FF&E at Bowie HS back into Program Contingency. |  | -750000
| Modernized Marshall MS - Additional funds need to complete furniture purchases. |  | 750000
CMD Adjustments
*Adjustments to complete Targeted Projects.
| Total January 2023 |  | -400000
December 2022 - 2017 Bond Budget Amendments
CMD Adjustments
*Adjustments to complete Targeted Projects.
| Total December 2022 |  | 0
November 2022 - 2017 Bond Budget Amendments
Contingency Transfers
| Eastside Vertical Modernization (Sanchez) - Additional funds required to close out the project and complete remaining scopes of work. |  | 500000
| Total November 2022 |  | 500000
October 2022 - 2017 Bond Budget Amendments
Contingency Transfers
| *Targeted Projects -Transferring cost savings from various projects back into Program Contingency. |  | -16457574
| Total October 2022 |  | -16457574
September 2022 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Brown -Transferring cost savings from project 190002-Brown back into Program Contingency. |  | -140000
| Total September 2022 |  | -140000
August 2022 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
July 2022 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Eastside HS @ Anderson - Additional funds need to complete change order. |  | 1000000
| Total July 2022 |  | 1000000
June 2022 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Eastside HS @ Anderson - Additional CAs / Slope assessment failure. |  | 350000
| Total June 2022 |  | 350000
May 2022 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
April 2022 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
March 2022 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Doss -Transferring cost savings from project 190001-Doss back into Program Contingency. |  | -400000
| Modernized Govalle -Transferring cost savings from project 190004-GOVAL back into Program Contingency. |  | -250000
| Modernized Menchaca -Transferring cost savings from project back into Program Contingency. |  | -90000
| Modernized Brown -Transferring cost savings from project 190002-Brown back into Program Contingency. |  | -80000
| Total March 2022 |  | -820000
February 2022 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized LBJ - Transferring cost savings from project 210001-LBJ back into Program Contingency. |  | -500000
| LASA move to Eastside - Covering technology, FF&E, and Branding items cost not included in original project budget. |  | 500000
| Modernized Murchison - Covering technology cost not included in original project budget. |  | 700000
| Modernized Govalle -Transferring cost savings from project 190004-GOVAL back into Program Contingency. |  | -200000
| Modernized Bear Creek -Transferring cost savings from project 190006-SWES back into Program Contingency. |  | -200000
| Modernized Doss -Transferring cost savings from project 190001-Doss back into Program Contingency. |  | -200000
| Modernized Brown -Transferring cost savings from project 190002-Brown back into Program Contingency. |  | -80000
| Total February 2022 |  | 20000
January 2022 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Eastside HS @ Anderson - Supplement funds for Design costs that exceed the PCB. |  | 250000
| Modernized Menchaca -Transferring cost savings from project back into Program Contingency. |  | -500000
| Transferring cost savings from Safety Consulting, Advertising, and Permits & Fees (3K, 3O, & 3P) programs back into Program Contingency. |  | -2783506
| Modernized Austin HS - Supplement funds for the GMP that exceed the PCB. |  | 2500000
| Modernized Blazier -Transferring cost savings from project back into Program Contingency. |  | -200000
| Modernized Ann Richards -Transferring cost savings from project back into Program Contingency. |  | -400000
| Modernized Casis - Covering technology cost not included in original project budget. |  | 750000
| Bowie HS Fine Arts & Athletics - Completing approved items for project. |  | 2200000
| Total January 2022 |  | 1816494
December 2021 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
November 2021 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
October 2021 - 2017 Bond Budget Amendments
Contingency Transfers
| Modernized Eastside HS @ Anderson - Supplement funds for the GMP that exceed the PCB. |  | 200000
| Total October 2021 |  | 200000
September 2021 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
August 2021 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
July 2021 - 2017 Bond Budget Amendments
| Galindo ES (Critical Facility Deficiencies) - The lowest bid received for HVAC improvements was higher than the amount currently budgeted for the work. |  | 230277
| Total July 2021 |  | 230277
June 2021 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
May 2021 - 2017 Bond Budget Amendments
Contingency Transfers
| Bowie - Supplement funds for the GMP that exceed the PCB. |  | 6341925
| LBJ - Supplement funds for the GMP that exceed the PCB. |  | -500000
| Rosedale - Supplement funds for the GMP that exceed the PCB. |  | 6801000
| Blazier - Supplement funds for the GMP that exceed the PCB. |  | -1000000
| LASA move to Eastside - Supplement funds for the GMP that exceed the PCB. |  | 932486
| Total May 2021 |  | 12575411
April 2021 - 2017 Bond Budget Amendments
Contingency Transfers
| McCallum - The contingency fund increase is due to Construction, A/E Services and Furniture costs for the Fine Arts Academy Reinvention (Project # 200010-005) |  | 1603537
| Total April 2021 |  | 1603537
March 2021 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
|  |  |  | 2500000 |  | 1125000
February 2021 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
January 2021 - 2017 Bond Budget Amendments
Contingency Transfers
| Sanchez - The contingency funds are being used for construction to replace the steel deck and roofing materials and labor on the two-story portion of the building. |  | 449213
0
| Total January 2021 |  | 449213 | 2820000 |  | -6726430
December 2020 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
November 2020 - 2017 Bond Budget Amendments
Contingency Transfers
| Bedichek - The contingency fund increase is due to the issues in the crawlspace and the added abatement scope of the hydronic piping in the crawlspace. |  | 600000
| LASA - The lowest bid received for the HVAC and Electrical work was higher than the amount currently budgeted for the work. |  | 350000
| Total November 2020 |  | 950000 | 2820000
October 2020 - 2017 Bond Budget Amendments
Contingency Transfers
| Brentwood - Supplement funds for the GMP that exceed the PCB, this was caused by market condition, added cost due to city requirements, and with no swing space budgeted. |  | 6156288
0
| Total October 2020 |  | 6156288 | 2820000 |  | -6726430
September 2020 - 2017 Bond Budget Amendments
Contingency Transfers
| Casis - Supplement funds for the GMP that exceeded the PCB, that was caused by market conditions, added cost due to city requirements, and with no swing space available which drove the duration of the project longer. |  | 8176136
| Govalle - This transfer is to fund the amount of CCO#1 for the unforeseen conditions when demolishing the building. |  | 500000
| Delco - Additional funding is requested to allow construction of two canopies, improve site drainage and make needed safety improvements at a failing, dangerous fence. |  | 193500
| Rodriguez - Increase to project construction budget due to the library water infiltrations issues. |  | 171709
| Sanchez - The contingency funds are being used for construction to replace the exterior envelope of the two-story portion of the building due to original construction and resulting moisture issues. |  | 589080
| LBJ - AISD already performed the envelope scope of the targeted project. Moving funds from Targeted project. |  | 1119701
| LBJ - AISD already performed the envelope scope of the targeted project. Moving funds to Modernization project. |  | -1119701
0
| Total September 2020 |  | 9630425 | 2820000 |  | -6726430
August 2020 - 2017 Bond Budget Amendments
Contingency Transfers
| Gullett - Original Construction Budget was $244,087, Novium Contract $329,000. Project had no contingency, TPC $304, 803.00. Current Project Cost 465,386.00 with Change Orders. Need approx. $160,500.00 to cover all expenses. |  | 160500
| NEECHS (Reagan) - During the construction phase, an inspection of replaced electrical panels revealed the absence of panel ground wires. Third party commissioning agent ACR strongly recommended installation of panel ground wires due to safety concerns and also recommended possible replacement of existing conductors, also due to safety concerns. Project engineer indicated that replacement of existing conductors and addition of ground wires was intended as part of the design. However, replacement of conductors and addition of ground wires was not mentioned on the drawings or in the project specifications. Contractor claims cost of feeder replacement and addition of ground wires was not included in their bid. |  | 200000
0
| Total August 2020 |  | 360500 | 2820000 |  | -6726430
July 2020 - 2017 Bond Budget Amendments
Contingency Transfers
| Eastside Vertical Modernization (Sanchez) - A budget increase of $857,835 from program contingency is needed to modify the FF&E (Furniture, Fixture and Equipment) budget, as well as additional construction costs for the project. The original FF&E budget amount did not align with the new furniture standards for modernizations projects. Also, the project increased in cost between the 90% and 100% Construction Developments due to final development of drawings and updates to AISD standard. |  | 857835
| Total July 2020 |  | 857835 | 2820000
April to June 2020 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
March 2020 - 2017 Bond Budget Amendments
Contingency Transfers
| Eastside Vertical Modernization (Sanchez) - Increase in budget to modernize Sanchez at the same standards as the other comprehensive projects. Additionally, Sanchez is on a unique site with narrow surrounding streets and City of Austin requirements. |  | 2463433 | 2500000 |  | 1125000
| Modernized Eastside HS @ Anderson - Transfer funds back into contingency since we are past a significant point in construction. |  | -1000000 | 2500000 |  | -3475644
| New Southwest ES - Due to the golden warbler, early release of the job package needed to be advertised, at the time market conditions were high and numbers for the project were unfavorable so we needed to add 2.8M to the project to ensure we carried money for early deployment and cover the costs of the unfavorable bid |  | 2862012 | 2500000 |  | 1000000
0
| Total March 2020 |  | 4325445 | 2820000 |  | -6726430
January 2020 - 2017 Bond Budget Amendments
Contingency Transfers
| Blazier Relief - Budget increased due to the construction of shell space to accommodate a future 7th grade build-out and allowance carried to facilitate schedule acceleration required due to a two month delay in the issuance of the site development permit. |  | 1375000 | 2500000 |  | 1125000
| LBJ Vertical Modernization (Norman) - Significant demolition and new construction required to meet Ed Specs. This was done instead of renovating as originally planned. |  | 5975644 | 2500000 |  | -3475644
| New Southwest ES - Budget increase due to the complexities of the site including complexities of construction atop Edwards limestone formation, existing karst features, grade change across the site, required extension of public utilities, and challenges of construction in a protected environmental habitat. |  | 1500000 | 2500000 |  | 1000000
| Allison ES-To supplement Critical Facility Deficiency budgets for negative balances. |  | 89042 | 940000 |  | 858772
| Bowie HS-To supplement Critical Facility Deficiency budgets for negative balances. |  | 209352 | 940000 |  | 730648
| Nelson Field /Bus Terminal-- The budget increased to cover the additional cost of added square footage needed due to overcrowding, and required temporary portable to displace staff during construction. |  | 218237 | 940000 |  | 858772
| O. Henry MS-To supplement Critical Facility Deficiency budgets for negative balances. |  | 81228 | 940000 |  | 858772
| Legal Services-To supplement Critical Facility Deficiency budgets at 14 schools for negative balances. |  | 97927
| Misc Operating Expenses-Program Level Contingency |  | 47222
| Misc Operating Expenses-Program Level Contingency |  | 46000
| Misc Operating Expenses-Program Level Contingency |  | 33932
| Misc Operating Expenses-Program Level Contingency |  | 21849
| Misc Operating Expenses-Program Level Contingency |  | 14764
| Misc Operating Expenses-Program Level Contingency |  | 8505 | 940000 |  | 858772
0
| Total January 2020 |  | 9718702 | 2820000 |  | -6726430
October 2019 - 2017 Bond Budget Amendments
Contingency Transfers
| Ann Richards - Increase in square footage to allow for new construction in line with district modernization principles instead of substantial renovation as planned, resulting in higher quality building, shorter schedule, and less disruption to the campus. |  | 2200000 | 2200000 |  | 0
| Murchison - Budget increased due to additional infrastructure required for future phases of modernization, including the connection between the existing building and new addition, drainage infrastructure, fire protection improvements, and additional temporary portables for onsite swing during construction. |  | 2500000 | 2500000 |  | 0
| Eastside Memorial HS - The cost of the delay, redesign, and historic materials salvage and reconstruction required a supplement to the budgeted from program contingency. The district coordinated with the Alumni Association to gain approval for demolition from the City of Austin Historic Landmark Commission. Historical preservation added a schedule delay in the project during design, resulting in a one school year delay to the project. |  | 8939000 | 8939000 |  | 0
0
| Total October 2019 |  | 13639000 | 13639000 |  | 0
August 2019 - 2017 Bond Budget Amendments
Contingency Transfers
| Correction for Bond Campus and Co-Curriculum Master Plan s/b Bond Carry Costs instead of Contingency Funds. |  | -802722
| Total August 2019 |  | -802722 | 2820000
July 2019 - 2017 Bond Budget Amendments | [5 empty] | 0
Contingency Transfers | [5 empty] | 0
| Misc Operating Expenses-Program Level Contingency |  | 549
| Construction Management-To supplement Critical Facility Deficiency budgets for negative balances. |  | 940000
| Construction Management-To supplement Legal Services budgets for negative balances. |  | 256895 | 940000 |  | 683105
| Misc Operating Expenses-Engineering Fees-Safety Consulting |  | 3996 | 223542 |  | 219546
| Total July 2019 |  | 1201440 | 1163542 |  | -37898
May 2019 - 2017 Bond Budget Amendments | [5 empty] | 0
Contingency Transfers | [5 empty] | 0
| Doss - The dual language program required an increase in the space program from the typical Ed. Spec. to accommodate additional classrooms. The final design relocated the building to the north east corner and increased it to three stories, utilizing the natural topography of the site. This resulted in saving significant green space and trees, but required demolishing and rebuilding the existing library, which had been planned to remain. The existing gym was able to be preserved due to its good condition, and location onsite. |  | 1300000 | 1300000 |  | 0
| Hill ES, Casey ES, & Allison ES-To supplement Critical Facility Deficiency budgets for negative balances. |  | 576321 | 164382 |  | -411939
| Bond Campus and Co-Curriculum Master Plan |  | 802722 | 389888 |  | -412834
0
| Total May 2019 |  | 2679043 | 1854270 |  | -824773
April 2019 - 2017 Bond Budget Amendments | [5 empty] | 0
Contingency Transfers | [5 empty] | 0
| T. A. Brown -Sustainable design for AEGB & LEED accreditation, master planned the outdoor learning area, and the installation of Thermal ICE storage HVAC system to dramatically reduce operations costs resulted in additional costs. Changes were in line with the school community’s desire to have a school that promotes “place-based environmental learning rooted in STEM.” |  | 1969000 | 1969000 |  | 0
| Govalle - Site constraints required additional improvements and costs required for an occupied site during construction. |  | 1500000 | 1500000 |  | 0
0
| Total April 2019 |  | 3469000 | 3469000 |  | 0
December 2018 to March 2019 - 2017 Bond Budget Amendments
No 2017 Bond Budget Amendments
November 2018 - 2017 Bond Budget Amendments | [5 empty] | 0
Contingency Transfers | [5 empty] | 0
| Menchaca - Complexities including site restrictions of building layout, additional traffic control, green scape areas, resulted in a three-building design, and extended internal traffic drive resulted in increased costs. |  | 3670000 | 3670000 |  | 0
0
| Total November 2018 |  | 3670000 | 3670000 |  | 0
|  | Total To Date: | 70652191 | 23795812 |  | -49238176
Notes: |  |  |  | 73822000 |  | Unallocated Budget for Program Contingency
All numbers are as of January 31, 2025.
*Projected transfers in December 2022 and January 2023 adjusted to reflect incurred transfers in February 2023.
Numbers may not add due to rounding. |  |  |  | #REF! |  | Budget Change for Program Contingency
|  |  |  | #REF! |  | Difference
|  |  |  | Hidden | Hidden | Hidden

## Bond Program Contingency
2017 Bond Program
Program Contingency Balance as of January 31, 2025
Report Month | Project Type | Transfer | Program Contingency Balance ($) | Program Contingency Balance (%)
November 2017 | Bond Initial Set-up | - | 73822000 | 100%
December 2019 | Modernization Projects | -19878000 | 49966239 | 67.68%
| Targeted Projects | -1516870
| Non-Construction | -2460891
January 2020 | Modernization Projects | -8850644 | 40247537 | 54.52%
| Targeted Projects | -761626
| Non-Construction | -106432
March 2020 | Modernization Projects | -4325445 | 35922092 | 48.66%
August 2020 | Modernization Projects | -857835 | 34703757 | 47.01%
| Targeted Projects | -360500
September 2020 | Modernization Projects | -500000 | 25662412 | 34.76%
| Targeted Projects | -8541345
October 2020 | Modernization Projects | -6745368 | 18917044 | 25.63%
January 2021 | Modernization Projects | -449213 | 17517831 | 23.73%
| Targeted Projects | -950000
April 2021 | Targeted Projects | -1603537 | 15914294 | 21.56%
May 2021 | Modernization Projects | -11642925 | 4271369 | 5.786%
August 2021 | Targeted Projects | -1162763 | 3108606 | 4.211%
October 2021 | Modernization Projects | -200000 | 2908606 | 3.94%
January 2022 | Modernization Projects | -4600000 | 1092112 | 1.479%
| Non-Construction | 2783506
February 2022 | Modernization Projects | 480000 | 1072112 | 1.452%
| Targeted Projects | -500000
March 2022 | Modernization Projects | 820000 | 1892112 | 2.563%
April 2022 | - | 0 | 1892112 | 2.563%
May 2022 | - | 0 | 1892112 | 2.563%
June 2022 | Modernization Projects | -350000 | 1542112 | 2.089%
July 2022 | Modernization Projects | -1000000 | 542112 | 0.7344%
August 2022 | Modernization Projects | 0 | 542112 | 0.7344%
September 2022 | Modernization Projects | 140000 | 682112 | 0.924%
October 2022 | Targeted Projects | 16457574 | 17139686 | 23.22%
November 2022 | Modernization Projects | -500000 | 16639686 | 22.54%
December 2022 | *Targeted Projects | 0 | 16639686 | 22.54%
January 2023 | Modernization Projects | 400000 | 17039686 | 23.08%
| *Targeted Projects | 0
February 2023 | Modernization Projects | -225000 | 741112 | 1.004%
| Targeted Projects | -16073574
March 2023 | - | 0 | 741112 | 1.004%
April 2023 | - | 0 | 741112 | 1.004%
May 2023 | Modernization Projects | 46900 | 788012 | 1.067%
June 2023 | - | 0 | 788012 | 1.067%
July 2023 | - | 0 | 788012 | 1.067%
August 2023 | - | 0 | 788012 | 1.067%
September 2023 | - | 0 | 788012 | 1.067%
October 2023 | Modernization Projects | -15375 | 693118 | 0.9389%
| Non-Construction | -79519
November 2023 | Modernization Projects | 2550338 | 1232870 | 1.67%
| Targeted Projects | -799922
| Non-Construction | -1210664
December 2023 | Modernization Projects | 2521831 | 3754701 | 5.086%
January 2024 | Modernization Projects | -10000 | 3744701 | 5.073%
February 2024 | Modernization Projects | -40000 | 951829 | 1.289%
| Targeted Projects | -2559872
| Non-Construction | -193000
March 2024 | - | 0 | 951829 | 1.289%
April 2024 | Targeted Projects | 1812284 | 2753460 | 3.73%
| Non-Construction | -10653
May 2024 | Modernization Projects | 29630 | 25282 | 0.03425%
| Targeted Projects | -2757808
June 2024 | Modernization Projects | 188999 | 947037 | 1.283%
| Targeted Projects | 737886
| Non-Construction | -5130
July 2024 | Targeted Projects | -340025 | 607012 | 0.8223%
August 2024 | - | 0 | 607012 | 0.8223%
September 2024 | Targeted Projects | -351000 | 256012 | 0.3468%
October 2024 | Targeted Projects | 2971220 | 3227232 | 4.372%
November 2024 | - | 0 | 3227232 | 4.372%
December 2024 | Targeted Projects | -72087 | 3155145 | 4.274%
January 2025 | Targeted Projects | 14664 | 3169809 | 4.294%
*Projected transfers in December 2022 and January 2023 adjusted to reflect incurred transfers in February 2023.
-70652191
| 2017 Bond Program Amendments Log Balance | 70652191
0

## Bond Program Previous Bonds
Previous Bond Authorized Support for 2017 Bond Projects
| CONSTRUCTION COSTS |  | Unallocated Budgets 2017 Bond | BUDGET AMENDMENTS |  | Total Current Budget | 2008 Bond | 2013 Bond | 2017 Bond | Total for Project
| Projects |  |  | Program Contingency Alloc Less than $50k | Program Contingency Alloc More than $50k
T. A. Brown
Project # 190002-BROWN
|  | Current Budget | 16499180 |  | 10751000 | 27250180 | 10751000 |  | 16499180 | 27250180
|  | Actuals |  |  |  |  | 10751000 |  | 16499182 | 27250182
|  | Commitments |  |  |  |  | 0 |  | 0 | 0
|  | Balance |  |  |  |  | 0 |  | -2 | -2
Menchaca
Project # 190003-MNCHC
|  | Current Budget | 9142911 |  | 23000000 | 32142911 |  | 23000000 | 9142911 | 32142911
|  | Actuals | [5 empty] | 23000000 | 9142911 | 32142911
|  | Commitments | [5 empty] | 0 | 0 | 0
|  | Balance | [5 empty] | 0 | 0 | 0
Bowie
Project # 190010-BOWIE
|  | Current Budget | 73734165 |  | 10000000 | 83734165 | 10000000 |  | 73734165 | 83734165
|  | Actuals |  |  |  |  | 10000000 |  | 73511804 | 83511804
|  | Commitments |  |  |  |  | 0 |  | 78823 | 78823
|  | Balance |  |  |  |  | 0 |  | 143538 | 143538
Total Bond Amounts
|  | Current Budget | 99376256 | 0 | 43751000 | 143127256 | 20751000 | 23000000 | 99376256 | 143127256
|  | Actuals |  |  |  |  | 20751000 | 23000000 | 99153897 | 142904897
|  | Commitments |  |  |  |  | 0 | 0 | 78823 | 78823
|  | Balance |  |  |  |  | 0 | 0 | 143536 | 143536
Notes:
All numbers are as of January 31, 2025.
Numbers may not add due to rounding.